## Task_Table1
WBS | Name | Cost | Resource_Initials
0 | Emergency SOS App | 1625920
1 | Planning | 132000
1.1 | Requirements & Scope | 66000
1.1.1 | Stakeholder & scope workshops | 30800 | P
1.1.2 | Requirements & NFRs baseline | 35200 | P
1.1.3 | Planning Go/No-Go (milestone) | 0
1.2 | Plans & Baselines | 66000
1.2.1 | Management plans (schedule/cost/risk/comms) | 35200 | P
1.2.2 | WBS, dependencies & set baselines (MSP) | 30800 | P
2 | Design | 343200
2.1 | UX & Prototypes | 190000
2.1.1 | UX research & wireframes | 91200 | U,P
2.1.2 | Design system & clickable prototype | 98800 | U,P
2.2 | Technical Design | 153200
2.2.1 | Solution architecture (app/backend/auth) | 46080 | S
2.2.2 | API & data model (+ NFR specs) | 107120 | S,P
2.2.3 | Design approved (milestone) | 0
3 | Development | 659200
3.1 | Foundation & Setup | 105600
3.1.1 | Repo/CI & environments | 33600 | D
3.1.2 | App skeleton & state management | 38400.000000000007 | S
3.1.3 | Security baseline & telemetry | 33600 | D
3.2 | Core Features | 343200
3.2.1 | SOS alert flow | 114400 | S,U,P
3.2.2 | GPS & live location | 114400 | P,S,U
3.2.3 | Contacts/templates & offline buffer | 114400 | P,S,U
3.3 | Integrations & Hardening | 210400
3.3.1 | SMS/Email gateway integration | 70400 | S,U
3.3.2 | Error logging & analytics | 67200 | Q,S
3.3.3 | Internal QA & polish | 72800 | P,Q
3.3.4 | Prototype complete (milestone) | 0
4 | Testing | 268160
4.1 | System Testing | 159520
4.1.1 | Functional & regression cycles | 88960 | P,Q,S
4.1.2 | Performance & security testing | 70560 | D,Q,S
4.2 | UAT & Stabilization | 108640
4.2.1 | UAT execution & feedback | 58240 | P,Q
4.2.2 | Bug-fix sprint & release candidate | 50400 | D,S
4.2.3 | Test sign-off (milestone) | 0
5 | Deployment | 189360
5.1 | Release Prep | 73360
5.1.1 | Store assets & compliance | 44400 | D,U,P,S
5.1.2 | Final build signing & docs | 28960 | D,P,Q,S
5.2 | Production Rollout | 116000
5.2.1 | Submission & prod rollout | 58000 | D,P,S
5.2.2 | Monitoring & handover | 58000 | P,D,S
5.2.3 | Go-Live sign-off (milestone) | 0
6 | Project Closure | 34000
6.1 | Close-out | 0
6.2 | Final report & financial close | 20400 | F,P
6.3 | Sponsor presentation & archive | 13600 | P,F
6.4 | Project closed (milestone) | 0