## Task_Table1
WBS | Name | Duration | Scheduled_Start | Finish_Date | Predecessors | Resource_Names | Cost
0 | Emergency SOS App | 225 days | Thu 1/1/26 | November 12, 2026 8:00 AM |  |  | 1625920
1 | Planning | 30 days | Thu 1/1/26 | February 11, 2026 5:00 PM |  |  | 132000
1.1 | Requirements & Scope | 15 days | Thu 1/1/26 | January 22, 2026 8:00 AM |  |  | 66000
1.1.1 | Stakeholder & scope workshops | 7 days | Tue 10/7/25 | January 9, 2026 5:00 PM |  | Project Manager | 30800
1.1.2 | Requirements & NFRs baseline | 8 days | Mon 1/12/26 | January 21, 2026 5:00 PM | 3 | Project Manager | 35200
1.1.3 | Planning Go/No-Go (milestone) | 0 days | Wed 1/21/26 | January 22, 2026 8:00 AM | 4 |  | 0
1.2 | Plans & Baselines | 15 days | Thu 1/22/26 | February 11, 2026 5:00 PM |  |  | 66000
1.2.1 | Management plans (schedule/cost/risk/comms) | 8 days | Thu 1/22/26 | February 2, 2026 5:00 PM | 5 | Project Manager | 35200
1.2.2 | WBS, dependencies & set baselines (MSP) | 7 days | Tue 2/3/26 | February 11, 2026 5:00 PM | 7 | Project Manager | 30800
2 | Design | 50 days | Thu 2/12/26 | April 23, 2026 8:00 AM | 1 |  | 343200
2.1 | UX & Prototypes | 25 days | Thu 2/12/26 | March 18, 2026 5:00 PM |  |  | 190000
2.1.1 | UX research & wireframes | 12 days | Thu 2/12/26 | February 27, 2026 5:00 PM | 8 | UI/UX Designer ,Project Manager | 91200
2.1.2 | Design system & clickable prototype | 13 days | Mon 3/2/26 | March 18, 2026 5:00 PM | 11 | UI/UX Designer ,Project Manager | 98800
2.2 | Technical Design | 25 days | Thu 3/19/26 | April 23, 2026 8:00 AM |  |  | 153200
2.2.1 | Solution architecture (app/backend/auth) | 12 days | Thu 3/19/26 | April 3, 2026 5:00 PM | 12 | Software Engineer | 46080
2.2.2 | API & data model (+ NFR specs) | 13 days | Mon 4/6/26 | April 22, 2026 5:00 PM | 14 | Software Engineer,Project Manager | 107120
2.2.3 | Design approved (milestone) | 0 days | Wed 4/22/26 | April 23, 2026 8:00 AM | 15 |  | 0
3 | Development | 90 days | Thu 4/23/26 | August 27, 2026 8:00 AM | 9 |  | 659200
3.1 | Foundation & Setup | 30 days | Thu 4/23/26 | June 3, 2026 5:00 PM |  |  | 105600
3.1.1 | Repo/CI & environments | 10 days | Thu 4/23/26 | May 6, 2026 5:00 PM | 16 | DevOps Engineer | 33600
3.1.2 | App skeleton & state management | 10 days | Thu 5/7/26 | May 20, 2026 5:00 PM | 19 | Software Engineer | 38400.000000000007
3.1.3 | Security baseline & telemetry | 10 days | Thu 5/21/26 | June 3, 2026 5:00 PM | 20 | DevOps Engineer | 33600
3.2 | Core Features | 30 days | Thu 6/4/26 | July 15, 2026 5:00 PM |  |  | 343200
3.2.1 | SOS alert flow | 10 days | Thu 6/4/26 | June 17, 2026 5:00 PM | 21 | Software Engineer,UI/UX Designer ,Project Manager | 114400
3.2.2 | GPS & live location | 10 days | Thu 6/18/26 | July 1, 2026 5:00 PM | 23 | Project Manager,Software Engineer,UI/UX Designer | 114400
3.2.3 | Contacts/templates & offline buffer | 10 days | Thu 7/2/26 | July 15, 2026 5:00 PM | 24 | Project Manager,Software Engineer,UI/UX Designer | 114400
3.3 | Integrations & Hardening | 30 days | Thu 7/16/26 | August 27, 2026 8:00 AM |  |  | 210400
3.3.1 | SMS/Email gateway integration | 10 days | Thu 7/16/26 | July 29, 2026 5:00 PM | 25 | Software Engineer,UI/UX Designer | 70400
3.3.2 | Error logging & analytics | 10 days | Thu 7/30/26 | August 12, 2026 5:00 PM | 27 | QA Tester,Software Engineer | 67200
3.3.3 | Internal QA & polish | 10 days | Thu 8/13/26 | August 26, 2026 5:00 PM | 28 | Project Manager,QA Tester | 72800
3.3.4 | Prototype complete (milestone) | 0 days | Wed 8/26/26 | August 27, 2026 8:00 AM | 29 |  | 0
4 | Testing | 30 days | Thu 8/27/26 | October 8, 2026 8:00 AM | 17 |  | 268160
4.1 | System Testing | 15 days | Thu 8/27/26 | September 16, 2026 5:00 PM |  |  | 159520
4.1.1 | Functional & regression cycles | 8 days | Thu 8/27/26 | September 7, 2026 5:00 PM | 30 | Project Manager,QA Tester,Software Engineer | 88960
4.1.2 | Performance & security testing | 7 days | Tue 9/8/26 | September 16, 2026 5:00 PM | 33 | DevOps Engineer,QA Tester,Software Engineer | 70560
4.2 | UAT & Stabilization | 15 days | Thu 9/17/26 | October 8, 2026 8:00 AM |  |  | 108640
4.2.1 | UAT execution & feedback | 8 days | Thu 9/17/26 | September 28, 2026 5:00 PM | 34 | Project Manager,QA Tester | 58240
4.2.2 | Bug-fix sprint & release candidate | 7 days | Tue 9/29/26 | October 7, 2026 5:00 PM | 36 | DevOps Engineer,Software Engineer | 50400
4.2.3 | Test sign-off (milestone) | 0 days | Wed 10/7/26 | October 8, 2026 8:00 AM | 37 |  | 0
5 | Deployment | 15 days | Thu 10/8/26 | October 29, 2026 8:00 AM | 31 |  | 189360
5.1 | Release Prep | 5 days | Thu 10/8/26 | October 14, 2026 5:00 PM |  |  | 73360
5.1.1 | Store assets & compliance | 3 days | Thu 10/8/26 | October 12, 2026 5:00 PM | 38 | DevOps Engineer,UI/UX Designer ,Project Manager,Software Engineer | 44400
5.1.2 | Final build signing & docs | 2 days | Tue 10/13/26 | October 14, 2026 5:00 PM | 41 | DevOps Engineer,Project Manager,QA Tester,Software Engineer | 28960
5.2 | Production Rollout | 10 days | Thu 10/15/26 | October 29, 2026 8:00 AM |  |  | 116000
5.2.1 | Submission & prod rollout | 5 days | Thu 10/15/26 | October 21, 2026 5:00 PM | 42 | DevOps Engineer,Project Manager,Software Engineer | 58000
5.2.2 | Monitoring & handover | 5 days | Thu 10/22/26 | October 28, 2026 5:00 PM | 44 | Project Manager,DevOps Engineer,Software Engineer | 58000
5.2.3 | Go-Live sign-off (milestone) | 0 days | Wed 10/28/26 | October 29, 2026 8:00 AM | 45 |  | 0
6 | Project Closure | 10 days | Thu 10/29/26 | November 12, 2026 8:00 AM | 39 |  | 34000
6.1 | Close-out | 5 days | Thu 10/29/26 | November 4, 2026 5:00 PM | 46 |  | 0
6.2 | Final report & financial close | 3 days | Thu 11/5/26 | November 9, 2026 5:00 PM | 48 | Finance/Admin Officer,Project Manager | 20400
6.3 | Sponsor presentation & archive | 2 days | Tue 11/10/26 | November 11, 2026 5:00 PM | 49 | Project Manager,Finance/Admin Officer | 13600
6.4 | Project closed (milestone) | 0 days | Wed 11/11/26 | November 12, 2026 8:00 AM | 50 |  | 0